PIC13/S2/1/Annex

Pacific Islands Action Plan on 
Climate Change and Health

A Roadmap for Implementation

1.	Implementation roadmap

1.1	Roadmap aims

The purpose of this roadmap is to guide Member States, the World Health Organization (WHO) and partners to operationalize the Pacific Islands Action Plan on Climate Change and Health. It recognizes the urgent need for both adaptation and mitigation actions. It links with key regional and global initiatives, such as Agenda 2030 and the Sustainable Development Goals (SDGs), the vision of Healthy Islands and other relevant strategies in the WHO Western Pacific Region.

1.2	Pacific Islands Action Plan framework

The Pacific Islands Action Plan has four strategic lines of action: (i) Empowerment: supporting health leadership in PICs to engage in national and international climate change discussions; (ii) Evidence: building the health argument for investment in climate change; (iii) Implementation: preparing for climate risks, building climate-resilient health systems and developing health-promoting mitigation policies; and (iv) Resources: facilitating greater and faster access to climate finance to support health. Under each strategic line of action, the Action Plan proposes a set of national and regional/global actions, both divided into short-term (by 2021) and long-term (by 2023) actions. There is also a set of supporting actions. Proposed indicators are divided into core and extended. This roadmap focuses on the identified short-term actions to be implemented by 2021, and on monitoring of all indicators.

2. 	Priority interventions to implement the Pacific Islands Action Plan

The Pacific Islands Action Plan identified 21 short-term actions for implementation by 2021. Because of the large number of actions (and activities to be conducted by Member States and by WHO), a key trigger action, that is, an action that would encompass the essential components to achieve each of the four strategic lines of action of the Action Plan, was identified. The trigger actions were identified during an Informal Working Group meeting to discuss implementation of the Pacific Islands Action Plan held in Suva, Fiji on 19-20 March, 2019. Within each set of activities listed below, those marked in bold are key activities to be achieved with the support of the additional activities listed.

2.1	Interventions on Empowerment

Focus: Supporting health leadership in Pacific Island Countries and Areas (PICs) to engage nationally and internationally.

Rationale: Health is increasingly recognized in climate discussions; nevertheless, it is still not routinely considered a priority – missing opportunities both to protect health and to mobilize health as an argument and success measure for climate action. Acting on empowerment will ensure the health argument is effectively incorporated into the official positions of Small Island Developing States (SIDS) groupings in global United Nations Framework Convention on Climate Change (UNFCCC) negotiations. Priority interventions by Member States and WHO are described below.

Outcome: The voice of health leaders, on behalf of the most vulnerable populations, becomes a driving force for adaptation in SIDS, and for mitigation by countries around the world.

Priority actions on Empowerment

Trigger action

Action 1.2. of Global Action Plan – Provide health sector inputs to UNFCCC and stakeholders and leading relevant national climate change processes (for example, national adaptation plans, national communications, nationally determined contributions).

National actions

Action N.1.1 – Support ministry of health engagement with the UNFCCC process and related forums, and participate in the National Adaptation Plans (NAPs) and similar processes – for example, nationally determined contributions – to include health (H-NAP):

| Priority activities by Member States | Priority activities by WHO |
| --- | --- |
| Strengthen the capacity of the health sector to manage climate change risk reduction with adaptation and mitigation actions through training and other capacity-building activities Set up a climate–health operational committee with intersectoral and civil society participation to manage the process. The health sector to take an active role in participating in key government meetings and in preparing relevant submissions to the UNFCCC and related processes. Ensure the active participation of the health sector in UNFCCC and related processes. Allocate financial resources in the national budget to support the implementation of the H-NAP. . | Support ministries of health in the preparation of key reports such as input to NAPs, though H-NAPS. Work with other United Nations agencies and donors to ensure health sector representation in relevant projects and programmes. Identify and provide/support training and capacity-building, where needed, including on UNFCCC-related issues for health leaders. |

Action N.1.2 – Identify, develop and encourage civil society organizations and nongovernmental organizations to be engaged in the climate change and health agenda, to better reach communities and implement action, considering their independence and flexible communication protocols:

| Priority activities by Member States | Priority activities by WHO |
| --- | --- |
| Develop an engagement strategy between the health sector and civil society to facilitate the assessment of integrated actions. Establish a mechanism for leaders from government, civil society and nongovernmental organizations to participate in climate change and health agenda discussions. Establish actions and spaces where civil society can participate in climate change adaptation and mitigation actions. | Support the health sector to identify and integrate actions with civil society. Work with other United Nations agencies to identify civil society representation in some of their relevant projects and programmes. |

Regional and global actions

Action R.1.1 – Ensure high-level engagement by including the SIDS Initiative in the ongoing agendas of the Pacific Health Ministers Meeting and the Asia-Pacific Regional Forum on Health and Environment, and in UNFCCC SIDS groupings, including the Alliance of Small Island States (AOSIS) and G77+China:

| Priority activities by Member States | Priority activities by WHO |
| --- | --- |
| Provide support for the full participation of the ministry of health in different forums related to climate change and health (for example, Pacific Health Ministers Meeting, Asia-Pacific Regional Forum on Health and Environment, Alliance of Small Island States (AOSIS), G77+China and UNFCCC SIDS groupings and other relevant forums). Prioritize funding in the annual budget to ensure the participation of the ministry of health in regional and international agendas. | Work with other United Nations agencies to support the participation of ministries of health in regional and international agendas, including preparatory meetings, side-events and physical presence in key events. |

Action R.1.2 – Include, in current regional mechanisms, terms of reference and strategies to keep the health sector engaged on the climate change agenda at all times, and to ensure that the climate change and health agenda is active in all related regional frameworks.

| Priority activities by Member States | Priority activities by WHO |
| --- | --- |
| Promote and support the active participation of the health sector in regional climate change agendas. Ensure funding is available and accessible to keep the health sector engaged in all regional and international climate change agendas. | Work with other United Nations agencies and international agencies to identify, in current regional frameworks, areas where the participation of the health sector needs strengthening. Work with regional organizations to support Member States to assess and monitor national actions on the climate change and health agenda. |

2.2	Interventions on Evidence

Focus: Building the health argument for investment.

Rationale: The health sector in many countries lacks the systematic economic evidence base that is necessary to make their case to potential investors to build climate-resilient health systems. Knowledge of the interlinkages between climate change and health is often limited and needs to be increased and constantly improved through research. Capacity to undertake research in the area of climate change and health in PICs needs to be strengthened. Priority interventions by Member States and WHO are described below.

Outcome: Ministries of health have the necessary health, environment and economic evidence to support scaled-up investment in climate change and health, identify priority investments, and monitor their success.

Priority actions on Evidence

Trigger action

Action 2.1 of Global Action Plan – In collaboration with the UNFCCC, develop or update national climate change and health country profiles for every SIDS.

National actions

Action N.2.1 – Ensure that vulnerability and adaptation assessments and climate change and health country profiles use a standardized approach, thus allowing for comparisons and sharing of methods and information, building on intraregional cooperation:

| Priority activities by Member States | Priority activities by WHO |
| --- | --- |
| Strengthen research cooperation and implementation of risk assessment actions related to climate change and health, including assessment of health sector vulnerability and capacity. Develop a mechanism to access available national and regional information on risks and vulnerabilities related to climate change and health, which have direct and indirect consequences on health. Map local risks and vulnerabilities to prioritize actions related to climate-related health emergencies and adaptation measures and mitigation policies, aiming at building or increasing work towards achieving climate-resilient health systems. Assess the national and local health sector capacity to cope and manage the impacts related to climate change. | Work with international agencies to support the development of standard approaches for vulnerability and adaptation assessments, based on best practices and intraregional cooperation. Identify or develop a mechanism or strategy to share information from every PIC to support health actions adopting best practices. |

Regional and global actions

Action R.2.1 – Identify, support and build on existing centres of excellence for increasing capacity, conducting assessments, data analysis and research, and implementing actions, including with organizations and universities that have regional mandates:

| Priority activities by Member States | Priority activities by WHO |
| --- | --- |
| Strengthen integrated regional cooperation among national agencies, academic institutions, the private sector and the ministry of health to build and assess the necessary information related to climate change and health risks. Build or support existing centres of excellence to share research, information, experiences and implement actions on adaptation measures and mitigation policies related to climate change to reduce risks to health. | Identify institutions to become official WHO collaborating centres. Stimulate cooperation between centres of excellence and national and regional organizations and institutions to provide information for adaptation and mitigation measures on climate change. Work with regional organizations and academic institutions to support Member States with evidence to build and strengthen climate-resilient health systems. |

Action R.2.2 – Implement a knowledge-sharing hub to provide health information and statistics on climate change and health for Pacific island countries and areas:

| Priority activities by Member States | Priority activities by WHO |
| --- | --- |
| Identify a national institution and/or government agency to be a focal point to work with other PICS to share knowledge, experiences and information to set up a knowledge-sharing hub. Develop a system to integrate information and statistics on climate change and health to provide evidence for action. Ensure funding availability to develop and provide effective support and technical assistance for the integration of shared information to support action on climate change adaptation and mitigation. | Work with other United Nations and international agencies to provide support to Member States to build or improve an existing knowledge-sharing hub on climate change and health risks. Share its experience, and the experiences of other countries and regions, with health-related knowledge hubs to support Member States. |

Action R.2.3 – Create a regional mechanism for WHO and the health sector to work with existing projects or entities such as the Secretariats of the Pacific Regional Environment Programme (SPREP) and the Pacific Community (SPC):

| Priority activities by Member States | Priority activities by WHO |
| --- | --- |
| Promote and support health sector participation in meetings on climate change of existing regional entities. Ensure the participation of the health sector in current projects, programmes and entities that work on climate change to ensure health adaptation measures and mitigation policies are included. | Work with other United Nations agencies to establish or support a regional mechanism for integrated cooperation and participation of Pacific ministries of health in existing projects, programmes and entities that work with climate change and health information and implementation of adaptation and mitigation actions. Establish formal relations with regional entities in the forms of letters of agreement and joint programmes of work to assist PICs, as needed. |

Action R.2.4 – Implement a regional climate and health information and research system allowing countries to have up-to-date WHO/UNFCCC climate change and health country profiles, shared regionally together with all relevant climate change and health research:

| Priority activities by Member States | Priority activities by WHO |
| --- | --- |
| Strengthen the regional policy dialogue among PICS, including with academic institutions in support of WHO/UNFCCC climate change and health country profiles and on climate change and health research. Work with academic institutions and the private sector to support regional information platform for climate and health to allow sharing of data and research, including best practices. | Work with UNFCCC to support PICS with regional climate change and health information and research. Support regional research (laboratories or institutions) to address climate-sensitive health outcomes. |

Action R.2.5 – Produce a regional roadmap that serves as an evidence base and prepare guidance to monitor and evaluate the effectiveness of designated priorities:

| Priority activities by Member States | Priority activities by WHO |
| --- | --- |
| Develop a strategic regional and national roadmap to support the building of evidence-based health actions, including contributions from academic institutions, civil society and the private sector. Develop normative guidance to monitor and evaluate the national plan on climate change and health. | Work with regional academic institutions to provide evidence-based information on the effectiveness of priorities and interventions. |

Action R.2.6 – Integrate climate change and health data in existing information systems such as the Pacific Public Health Surveillance Network (PPHSN) and the Pacific Climate Change Portal (PCCP):

| Priority activities by Member States | Priority activities by WHO |
| --- | --- |
| Establish agreements and mechanisms to be able to access and include climate change and health data in existing information systems. | Work with Member States to ensure access to existing information systems and to ensure key climate and health information is included in such systems. |

2.3	Interventions on Implementation

Focus:	Preparedness for climate risks, building climate-resilient health systems, and health-promoting mitigation policies.

Rationale: There is an identified need to strengthen the role of the health sector in promoting health co-benefits of climate change mitigation actions that are implemented by those sectors more responsible for global warming. Actions will build on the experience gained in climate and health adaptation projects around the world, applying WHO’s Operational Framework for Building Climate-Resilient Health Systems. Priority interventions by Member States and WHO are described below.

Outcome: Transformational change occurs in health systems, by promoting a culture of disease prevention, building the climate resilience of health systems and maximizing the health co-benefits of climate change mitigation policies.

Priority actions on Implementation

Trigger action

Action 3.1 of Global Action Plan – Support countries through regional frameworks to build climate-resilient health systems.

National actions

Action N.3.1 – Support the WHO/UNFCCC Climate and Health Country Profile Project as the mechanism for the implementation and monitoring of this Plan of Action:

| Priority activities by Member States | Priority activities by WHO |
| --- | --- |
| Commit to participate in the climage change and health country profiles project by providing information to WHO and performing analyses and follow-up of actions, including regular updates, in order to have a reliable system to monitor the Pacific Islands Action Plan and its implementation at the national level. Establish a system to monitor actions on a regular basis, taking the first country profile as the baseline to monitor and evaluate the effectiveness of interventions. Build capacity for the health sector to perform this task instead of external consultants. | Work with UNFCCC and Member States to ensure that climate change and health country profiles are completed and regularly updated. |

Action N.3.2 – Support training to build awareness and knowledge of the UNFCCC agreements, including the Paris Agreement, for the ministry of health:

| Priority activities by Member States | Priority activities by WHO |
| --- | --- |
| Ensure financial support to train leaders from the ministry of health on subjects related to UNFCCC agreements. Ensure active participation and financial support of the health sector to participate in the UNFCCC and related training and capacity-building activities. | Work with other United Nations agencies to support and strengthen cooperation to build awareness and knowledge of the climate change and health agendas and related processes for Member States. WHO to facilitate discussions among delegates at the Conference of the Parties (COP) to allow dialogue and synergies. |

Action N.3.3 – Develop and implement programmes and training to promote the transition to a culture of disease prevention both by people and by the health system:

| Priority activities by Member States | Priority activities by WHO |
| --- | --- |
| Develop educational programmes for people and health staff to promote healthy habits, disease prevention and climate risk reduction actions. Develop a new approach for health promotion for a transition to a culture of disease prevention, including the training of health professionals and leaders of academic institutions and civil society. Mobilize funds to strengthen national programmes of primary health care to implement actions to assist people including in remote areas. Identify workforce needs and work with universities to develop training courses, including on early warning systems and integrated health surveillance | Work with regional centres of excellence and other institutions in developing appropriate training. Support Member States in educational campaigns related to the promotion of a culture of disease prevention. |

Action N.3.4 – Conduct baseline assessment and develop mitigation plans to reduce greenhouse gas (GHG) emissions from energy, food, transportation and procurement within the health sector:

| Priority activities by Member States | Priority activities by WHO |
| --- | --- |
| Develop and implement mitigation plans from each sector within the health sector (i.e. energy, food, transportation and procurement), including the private sector, into the national plan for climate change to reduce GHG emissions, based on a baseline assessment. Assess GHG emissions by the health sector and develop the baseline to monitor actions. Develop guidance for green health-care facilities. | Work with international agencies to provide information to support baseline assessments and setting mitigation plans. Provide guidance on e-health and telemedicine. |

Action N.3.5 – Promote an enabling environment to identify and update climate change and health–related policies, standards and legislation:

| Priority activities by Member States | Priority activities by WHO |
| --- | --- |
| Establish, by legislation or policy, where relevant, an intersectoral national committee on climate change and health to discuss the ongoing impacts of sectoral policies in health protection. Promote standards and legislation to reduce GHG emissions and strategies to assess health benefits. | Support the health sector in Member States by identifying international best practice and provide guidance on climate change and health–related policies that can be translated to PICs. Identify best practice to reduce GHG emissions from the health sector, thus ensuring the sector leads by example. |

Regional and global actions

Action R.3.1 – Strengthen current regional frameworks to support countries to implement actions to build climate-resilient health systems:

| Priority activities by Member States | Priority activities by WHO |
| --- | --- |
| Ensure health sector participation in all regional frameworks for climate change actions. Promote capacity-building for developing and implementing actions to build climate-resilient health systems. | Work with Member States and advocate for United Nations, international agencies and funding agencies to support the implementation of PICS frameworks related to climate-resilient health systems. Support south-south cooperation and interregional exchanges (for example, with Caribbean countries). |

2.4	Interventions on Resources

Focus: Facilitating access to climate and health finance.

Rationale: The SIDS Initiative recognizes that a significant change in current health vulnerability of the populations of SIDS will not be possible without access to sufficient financial resources. Ministers of health have prioritized the need to expand and diversify the funding streams potentially available to build health resilience to climate change. Priority interventions by Member States and WHO are described below.

Outcome: The current level of financial investment in climate change and health in SIDS is tripled.

Priority actions on Resources

Trigger action

Action 4.1 of Global Action Plan – Lead a process to identify new and innovative forms of funding and resource mobilization mechanisms.

National actions

Action N.4.1 – Strengthen national leadership, advocacy and mechanisms to establish a clear process to access climate change and health financing:

| Priority activities by Member States | Priority activities by WHO |
| --- | --- |
| Strengthen existing modalities for accessing climate change finance by providing open access to the health sector. Utilize data on cost of action and inaction related to climate change and health. Ensure health sector participation in the climate change and health agendas and related processes to access information and knowledge. | Support Member States to access climate change and health financing. |

Action N.4.2 – Implement mechanisms with development partners to overcome current complexities in accessing funds by building capacity of in-country focal points and advocating greater simplification and transparency in the process:

| Priority activities by Member States | Priority activities by WHO |
| --- | --- |
| Integrate health into existing mechanisms to facilitate cooperation with funding development partners related to the climate change and health agendas. Include health in capacity-building workshops and locally held meetings of donors and funders Continue to advocate for simple and transparent processes. | Work with international agencies to facilitate and support access to funds for the local health sector to strengthen capacity for climate resilience. Mobilize partners to support funding to train national focal points on assessment of climate change adaptation and mitigation action needs for the preparation of funding proposals. |

Regional and global actions

Action R.4.1 – Explore regional opportunities to increase access to funds while advocating for the health sector to be a direct recipient of climate funds:

| Priority activities by Member States | Priority activities by WHO |
| --- | --- |
| Strengthen regional cooperation to ensure the identification and implementation of priority actions in the health sector that need access to funds. Advocate actions to ensure funding for the health sector to be integrated into national climate change agendas and related processes; and for health to be the lead implementing agency for health projects in countries. | Work with regional and international agencies to promote and support the PICs health sector to have access to funds to implement their climate change mitigation and adaptation actions and build climate-resilient health systems. |

Action R.4.2 – Support accreditation of WHO for the Global Environment Facility (GEF) and the Green Climate Fund (GCF):

| Priority activities by Member States | Priority activities by WHO |
| --- | --- |
| Intervene, where feasible, with climate change agendas and related programmes, such as GEF and GCF, in support of WHO accreditation, for better implementation of the climate change and health agenda in the Pacific. | Continue working towards GEF and GCF accreditation, while also working with development partners and funding agencies to mobilize funds to support PICs. |

3. Budget estimates, resource mobilization and timeline for implementation

3.1	Budget estimates

The total financial investment to implement the identified short-term actions (to 2021) will depend on the availability of trained government staff, and the availability in each country of support groups such as academic institutions, nongovernmental organizations and other stakeholders. Table 1 lists actions to be implemented by 2021, together with an estimate of funds following a scale of: low (under US$ 100 000); medium (over US$ 100 000 and under US$ 250 000); and high (over US$ 250 000 and under US$ 1 million). These estimates are approximate and will differ according to countries. If we consider the highest estimates for each category, the total implementation cost would be US$ 4.65 million per country to implement 21 actions by the end of 2021. Broken down by strategic line of action, the estimated costs would be US$ 1 million for Empowerment; US$ 1.9 million for Evidence; US$ 1.2 million for Implementation; and US$ 550 000 for Resources. As this is the high end of the budget, it would be feasible to work on a budget of about half this amount.

Table 1. Actions and budget estimates

| Actions to 2021 | Expected costs |
| --- | --- |
| Priority actions on Empowerment |  |
| Action N.1.1 Support ministry of health engagement with the UNFCCC process and related forums, and participate in the national adaptation plans (NAPs) and similar processes – for example, nationally determined contributions – to include health (H-NAP). | Medium |
| Action N.1.2 Identify, develop and encourage civil society organizations and nongovernmental organizations to be engaged in the climate change and health agenda, to better reach communities and implement action, considering their independence and flexible communication protocols. | Medium |
| Action R.1.1 Ensure high-level engagement by including the SIDS Initiative in the ongoing agendas of the Pacific Health Ministers Meeting and the Asia-Pacific Regional Forum on Health and Environment, and in UNFCCC SIDS groupings, including the Alliance of Small Island States (AOSIS) and G77+China. | Medium |
| Action R.1.2 Include, in current regional mechanisms, terms of reference and strategies to keep the health sector engaged on the climate change agenda at all times, and to ensure that the climate change and health agenda is active in all related regional frameworks. | Medium |
| Priority actions on Evidence |  |
| Action N.2.1 Ensure that vulnerability and adaptation assessments and profiles for each country use a standardized approach, thus allowing for comparisons and sharing of methods and information, building on intraregional cooperation | Medium |
| Action R.2.1 Identify, support and build on existing centres of excellence for increasing capacity, conducting assessments, data analysis and research, and implementing actions, including with organizations and universities that have regional mandates | High |
| Action R.2.2 Implement a knowledge-sharing hub to provide health information and statistics on climate change and health for Pacific island countries and areas | Low |
| Action R.2.3 Create a regional mechanism for WHO and the health sector to work with existing projects or entities such as the Secretariats of the Pacific Regional Environment Programme (SPREP) and the Pacific Community (SPC) | Low |
| Action R.2.4 Implement a regional climate and health information and research system allowing countries to have up-to-date WHO–UNFCCC Climate change and health country profiles, shared regionally together with all relevant climate change and health research | Medium |
| Action R.2.5 Produce a regional roadmap that serves as an evidence base and prepare guidance to monitor and evaluate the effectiveness of designated priorities | Low |
| Action R.2.6 Integrate climate change and health data in existing information systems such as the Pacific Public Health Surveillance Network (PPHSN) and the Pacific Climate Change Portal (PCCP) | Low |
| Priority actions on Implementation |  |
| Action N.3.1 Support the WHO–UNFCCC Climate and Health Country Profile Project as the mechanism for the implementation and monitoring of this Plan of Action | Low |
| Action N.3.2 Support training to build awareness and knowledge of the UNFCCC agreements, including the Paris Agreement, for the ministry of health | Medium |
| Action N.3.3 Develop and implement programmes and training to promote the transition to a culture of disease prevention both by people and by the health system | Medium |
| Action N.3.4 Conduct baseline assessment and develop mitigation plans to reduce greenhouse gas (GHG) emissions from energy, food, transportation and procurement within the health sector | Low |
| Action N.3.5 Promote an enabling environment to identify and update climate change and health–related policies, standards and legislation | Medium |
| Action R.3.1 Strengthen current regional frameworks to support countries to implement actions to build climate-resilient health systems | Medium |
| Priority actions on Resources |  |
| Action N.4.1 Strengthen national leadership, advocacy and mechanisms to establish a clear process to access climate change and health financing | Medium |
| Action N.4.2 Implement mechanisms with development partners to overcome current complexities in accessing funds by building capacity of in-country focal points and advocating greater simplification and transparency in the process | Low |
| Action R.4.1 Explore regional opportunities to increase access to funds while advocating for the health sector to be a direct recipient of climate funds | Low |
| Action R.4.2 Support accreditation of WHO for the Global Environment Facility (GEF) and the Green Climate Fund (GCF) | Low |

3.2	Resource mobilization

Resource mobilization is one immediate priority for the implementation of the Pacific Islands Action Plan. Specifically, Action N.4.1, Strengthen national leadership, advocacy and mechanisms to establish a clear process to access climate change and health financing, needs to be implemented by all countries in 2019. To achieve this action, there is a role for all key stakeholders, with a leading role for governments, WHO, international agencies and funding agencies, and a supporting role for academic institutions, civil society and the private sector.

To accomplish this action, Member States need to implement the following activities: (1) establish evidence-based data on cost of action and inaction related to climate change and health; (2) work with academic institutions to support the establishment of evidence related to process; and (3) ensure health sector participation in the climate change and health agendas and related processes to access information and knowledge. In turn, WHO will work with funding agencies to support Member States to access climate change and health financing.

The WHO Regional Office for Europe developed an economic analysis tool to support Member States in their climate change adaptation plans. The tool aims to help countries, and specifically the health sector, to analyse the costs of health damages, and the costs and benefits from adaptation measures implemented. This tool can be useful for PICs to estimate the costs of action and inaction and used as an argument for resource mobilization.

Academic institutions, WHO and international agencies can play an important role in building capacity to perform economic analyses of the health impacts of climate change. It is necessary to build capacity at the national and regional levels for all countries to have equal opportunities for seeking funding. Participation of health leaders in key regional and global meetings, such as those of the UNFCCC, is important for advocacy, for creating awareness among partners, and also for the health sector to build its capacity.

3.3	Timeline for implementation

The timeline for implementation of short-term actions covered in this roadmap is for 36 months, starting in January 2019., There has already been some progress since the launch of the Pacific Islands Action Plan in May 2018. This section only addresses new or incomplete activities to be addressed (Table 2). Most actions in the Pacific Islands Action Plan are ongoing. The Gantt chart shows the times where particular emphasis and support should be provided for the action to begin.

Table 2. Timeline for implementation of the Pacific Islands Action Plan

| Actions | Months |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 |
| R.2.5 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| N.2.1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| N.3.1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| N.1.1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| N.4.1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| R.4.2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| N.3.2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| N.1.2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| R.2.1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| N.4.2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| R.1.1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| R.1.2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| R.2.2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| R.2.3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| R.2.6 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| R.2.4 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| N.3.3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| R.4.1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| N.3.4 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| N.3.5 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| R.3.1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

Legend:

|  | Empowerment, National |  |  | Empowerment, Regional/Global |
| --- | --- | --- | --- | --- |
|  | Evidence, National |  |  | Evidence, Regional/Global |
|  | Implementation, National |  |  | Implementation, Regional/Global |
|  | Resources, National |  |  | Resources, Regional/Global |

4.	Next steps

The Pacific Islands Action Plan is realistic within the constraints of insufficient resources. Achievement of the first phase, to be completed by the end of 2021, is feasible but will require a strong commitment from countries and international agencies.

This Roadmap will be revised annually to identify areas requiring attention. This first draft was reviewed by an informal working group in March 2019. A revised version will be presented to the Thirteenth Pacific Health Ministers Meeting in August 2019 for consideration.

Pacific islands action plan on climate change and health. Manila: World Health Organization Regional Office for the Western Pacific; 2018.

Operational framework for building climate resilient health systems. Geneva: World Health Organization; 2015.